## Report
Date: | Q2 2018
Capex Reporting - Quarterly Updates
Deliverable?
Schedule RAG |  |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022
| Notes (e.g. explanation of schedule change) | Project |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  | T1 and T2 CUSS Check-in Facilities |  | Schedule | bar: 2016 Q1 to 2016 Q3; 2017 Q1 to 2017 Q2; 2017 Q4 to 2018 Q2
Actual/Forecast
|  | Pier 1 Extension |  | Schedule | bar: 2016 Q1 to 2017 Q2
Actual/Forecast
|  | South Apron PBZ |  | Schedule | bar: 2016 Q2 to 2017 Q4
Actual/Forecast
|  | T1 and T2 Immigration Facilities |  | Schedule | bar: 2017 Q3 to 2019 Q3
Actual/Forecast
|  | T2 Level 15 Bus Gates | Y | Schedule | bar: 2018 Q4 to 2020 Q4
Actual/Forecast
|  | South Apron Stands Phase 1 |  | Schedule | bar: 2016 Q1 to 2017 Q1
Actual/Forecast
|  | Apron 5H and Taxiway Rehabilitation | Y | Schedule | bar: 2016 Q3 to 2020 Q2
Actual/Forecast
|  | Upgrade and Realignment of Stands 101-104 |  | Schedule | bar: 2017 Q2 to 2018 Q2
Actual/Forecast
|  | Hangar 1 and 2 Stands |  | Schedule | bar: 2017 Q3 to 2019 Q4
Actual/Forecast
|  | West Apron Stands |  | Schedule | bar: 2018 Q1 to 2019 Q1
Actual/Forecast
|  | Pier 2 Underpass |  | Schedule | bar: 2017 Q3 to 2019 Q3
Actual/Forecast
|  | Pier 3 Underpass |  | Schedule | bar: 2017 Q4 to 2018 Q1
Actual/Forecast
|  | West Apron Surface Access |  | Schedule | bar: 2017 Q1 to 2019 Q2
Actual/Forecast
|  | Advanced Visual Docking Guidance (A-VDGS) | Y | Schedule | bar: 2017 Q4 to 2020 Q3
Actual/Forecast
|  | Fixed Electrical Ground Power (FEGP) | Y | Schedule | bar: 2017 Q4 to 2019 Q4
Actual/Forecast
|  | South Apron Stands Phase 2 |  | Schedule | bar: 2018 Q1 to 2022 Q1
Actual/Forecast
|  | Apron-Wide CCTV |  | Schedule | bar: 2017 Q4 to 2019 Q2
Actual/Forecast
|  | Link 3 Extension Taxiway | Y | Schedule | bar: 2017 Q2 to 2021 Q1
Actual/Forecast
|  | Realignment of Taxiway A | Y | Schedule | bar: 2017 Q2 to 2021 Q1
Actual/Forecast
|  | Dual Taxiway F | Y | Schedule | bar: 2017 Q2 to 2021 Q1
Actual/Forecast
|  | Link 6 Extension Taxiway |  | Schedule | bar: 2017 Q2 to 2019 Q1
Actual/Forecast
|  | South Apron Taxiway Widening | Y | Schedule | bar: 2018 Q1 to 2021 Q2
Actual/Forecast
|  | Runway 10 Line-Up Points | Y | Schedule | bar: 2018 Q3 to 2021 Q3
Actual/Forecast
|  |  |  | Code: | 2016 Q2: Feasibility
Design/Procurement
Construction
Handover

## Notes
Dublin Airport is required to update the 'Actual/Forecast' rows in the GANNT chart below at the end of each quarter, with an up to date forecast as to the progression of the project, including schedule RAG (Red, Amber, Green) and publish. Green means the project is at or ahead of schedule AND expected to be completed on time, Amber that the project is less than six months behind schedule OR that the expected delivery date is less than six months later than scheduled, Red means it is more than six months behind schedule OR expected to be delivered more than six months late.
Where a project is deferred, delayed, prioritised or no longer on schedule for another reason, the reasons need to be detailed in the notes section.